## Sheet1
| Task | Timeline
1 | Create table according to the schema and understand the project | 6
Admin section (activity listing and add ,edit,delete and copy of activity)
2 | Provide activity listing
| in the left menu in the config show the acvity list on click on this show listing page. show the activity type name, start date, end date,edit (if the activity is not started),copy this activity | 4
| Provide add new activity button on the top | 0.5
3 | on the click of new activity button
Section 1:
| 1)Show text box for the activity name,code and heading | 1
| 2)Provide calendar for start date and end date of the activity | 1
| 3)Provide the index page content yes or no if yes then provide ckeditor for insert the index page content also provide add more button to add more index page | 4
Section 2: add more category section
| 1) Provide activity add section in this section provide activity name,multi select class dropdown,Fees text box,also provide the activyt batch time (add more),show the age group yes or no | 5
| 2. Provide the add more activity and delete option also | 3
Section 3:
| 1)Provide the maximum and minimum no of activity dropdown | 2
| 2)Provide the email content ckeditor text filed, subject and add cc and bcc field | 3
| 3)provide the submit and preview button functionality on click on preview show the form in the popup | 5
| 4) provide the radion button to send the delaration form yes or no | 0.5
| 5) on click of yes provide the input ck editor to input the declaration form content | 2
4 | onclick on submit save the data into the database | 5
5 | provide edit option for the activity type form if it is not started | 6
6 | Provide delete option for the activity type form if it the activity is not started | 1
7 | Copy of activity form (inthis provide whole the form with the data fillup admin can edit the data on the save create new activity type) | 6
8 | provide mis for activity report in this show the transaction in the table(student name, amount, date ,airpay id) , show receipt and send resend receipt option | 5
9 | Provide the filter for start date,end date , airpay id , actity type name filter | 4
10 | provide download MIS report option on click of this provide the detail mis report ( in this provide activity detail also and other student information also) | 4
11 | Provide checkbox against each student and also provide select all option to send the receipt to the student | 3
12 | Admin registration form
| 1.Provde the roll no option | 2
| 2.on the roll no input prefilled the first name,middle name,last name,contact no and mobile and class and section | 2
| 3.show the activity for the student according to the roll no and class | 1
| 4.provide the payment option dorpown(with the option of the pos) | 3
| 5. Depend upon the activity selection show the amount and according to the payment option show the payable amount | 2
| 6. on click of the submit button check all the data enter or not check also for minimum and max activity | 1
| 7. On submit save the data and according the payment option pass the data and chmod on the payment page if the payment option is pos then call the create api and save the data and complete the transaction process | 4
| 8. on the complete of the payment save the data in to the database | 1
| 9. Send email to the parent with the receipt | 1
| 10. Show receipt | 2
| 11. If the send declaration form is yes then send that in attachment of email | 3
Student login (student section)
13 | student registration form
| 1. If the student class is configure for the activity then show the register activity button | 1
| 2. All the details show non editable like first name,middle name,last name, email ,mobile, provide input for the alternate contact no | 1
| 3. depend upon the class show the activity and also provide the fee against this activity if fees not enter than provide text box for it | 2
| 4. Provide the payment option dropdown | 1
| 5. Depend upon the activity selection show the amount and according to the payment option show the payable amount | 0.5
| 6. on click of the submit button check all the data enter or not check also for minimum and max activity | 0.5
| 7. On submit save the data and according the payment option pass the data and chmod on the payment page | 1
| 8. on the complete of the payment save the data in to the database | 0.5
| 9. Send email to the parent with the receipt | 0.5
| 10. Show receipt | 0.5
14 | In the report section show the activity tab and show all the activity which for the student register also provide option for the view receipt option | 5
15 | on the end date of the activity disable the register button | 1